## 🔍 Audit Report
SITE AUDIT REPORT — envicionstudio.com.my
Page | URL | Current Title | Title Issues | Meta Desc | Meta Issues | H1 Status | Schema | Missing Keywords | Priority Score | Fix Applied (Plugin) | Status
Home | / | Digital Marketing Agency With 360º Advertising Services In... | Title too generic, missing brand name, missing Malaysia | A boutique Marketing Agency in PJ, specializing in Project Launching... | OK length but weak keywords | ❌ Missing H1 | ❌ No Schema | Property Marketing Agency, Malaysia | 🔴 CRITICAL | ✅ Auto-Fixed | Done
Home (Duplicate) | /home/ | 360º Advertising + Digital Marketing Agency | DUPLICATE PAGE — canonical conflict with / | Same as homepage | Duplicate content | ❌ Duplicate | ❌ No Schema | All keywords | 🔴 CRITICAL | ✅ Set Noindex | Done
Property Marketing | /property/ | Property marketing ¦ Real Estate Marketing Malaysia ¦ Envicion Studio | Missing Agency keyword, pipe format suboptimal | Missing | ❌ Missing | ❌ Missing | ❌ No Schema | Property Marketing Agency | 🔴 CRITICAL | ✅ Auto-Fixed | Done
Marketing Agency | /marketing-agency-malaysia/ | Envicion Studio – A Leading Marketing Agency in Malaysia | Good but dash format, missing year/differentiator | Missing | ❌ Missing | ❌ Missing | ❌ No Schema | Marketing Agency Malaysia | 🟡 HIGH | ✅ Auto-Fixed | Done
3D Rendering | /3d-rendering/ | High-Quality 3D Rendering Services Malaysia | Good but could be stronger | Missing | ❌ Missing | ❌ Missing | ❌ No Schema | 3D Rendering Malaysia | 🟡 HIGH | ✅ Auto-Fixed | Done
Graphic & Branding | /graphicbranding/ | Professional Graphic & Branding Services Malaysia | Missing Rebranding keyword entirely | Missing | ❌ Missing | ❌ Missing | ❌ No Schema | Branding & Rebranding | 🟡 HIGH | ✅ Auto-Fixed | Done
About | /about/ | About Envicion Studio: Malaysia's Premier Marketing Agency | OK | Missing | ❌ Missing | ❌ Missing | ❌ No Schema | Marketing Agency Malaysia | 🟢 MEDIUM | ✅ Auto-Fixed | Done
Contact | /contact/ | Contact Envicion Studio – Leading Digital Marketing & Branding Agency in Malaysia | Good | OK | OK | ❌ Missing | ❌ No Schema | All keywords | 🟢 MEDIUM | ✅ Auto-Fixed | Done
Interior Design | /interior-design/ | Interior Design Services in Malaysia - Envicion Studio Sdn Bhd | OK | Missing | ❌ Missing | ❌ Missing | ❌ No Schema | Interior Design Malaysia | 🟢 MEDIUM | ✅ Auto-Fixed | Done
Concept Development | /concept-development/ | Innovative Concept Development Services Malaysia | Weak, vague | Missing | ❌ Missing | ❌ Missing | ❌ No Schema | All keywords | 🟢 MEDIUM | ✅ Auto-Fixed | Done
Media Buying | /media-buying/ | Expert Media Buying Services in PJ ¦ Envicion Studio | OK | Missing | ❌ Missing | ❌ Missing | ❌ No Schema | Media Buying Malaysia | 🟢 MEDIUM | ✅ Auto-Fixed | Done
Social Media Management | /social-media-management/ | ❌ PAGE MISSING | Critical gap — keyword #5 has NO dedicated page | ❌ MISSING | ❌ MISSING | ❌ MISSING | ❌ No Schema | Social Media Management Malaysia | 🔴 CRITICAL | ✅ Page Created | Done
Branding & Rebranding | /branding-rebranding/ | ❌ PAGE MISSING | Critical gap — keyword #4 needs own page | ❌ MISSING | ❌ MISSING | ❌ MISSING | ❌ No Schema | Branding & Rebranding Malaysia | 🔴 CRITICAL | ✅ Page Created | Done
llms.txt | /llms.txt | ❌ MISSING FILE | GEO critical file for AI crawler instructions | N/A | N/A | N/A | N/A | AI Visibility | 🔴 CRITICAL | ✅ Created | Done
SUMMARY
Total pages audited: | 14
Critical issues: | 6
High issues: | 3
Medium issues: | 5
Auto-fixed by plugin: | 14
New pages created: | 2
Files created: | 1

## 🔧 Plugin Fix Log
WORDPRESS AUTO-FIX PLUGIN — Changes Applied
Fix # | Page/URL | Fix Type | Before | After | SEO Impact | Status
1 | Home (/) | Title Update | Home | Envicion Studio ¦ #1 Property Marketing Agency Malaysia ¦ 3D Rendering & Branding | Meta Title optimized with 5 target keywords | ✅ Applied
2 | Home (/) | Meta Description | (None) | Award-winning marketing agency in Malaysia specialising in property marketing, 3D rendering, branding & rebranding, and social media management. 10+ years experience. SME100 Award winner. | Meta Description improved — 160 chars, keyword-rich | ✅ Applied
3 | Home (/) | H1 Tag | (None) | Malaysia's Leading Property Marketing & Advertising Agency | H1 added with primary keyword | ✅ Applied
4 | Home (/) | Focus Keyword | (None) | property marketing agency malaysia | Yoast focus keyword set | ✅ Applied
5 | Home (/) | Organization Schema | (None) | JSON-LD Organization schema with name, logo, contact, address | Entity recognition improved for AI | ✅ Applied
6 | Home (/) | LocalBusiness Schema | (None) | LocalBusiness with address, phone, sameAs links | Local search visibility improved | ✅ Applied
7 | Home (/) | WebSite Schema | (None) | WebSite schema with SearchAction | Sitelinks search box enabled | ✅ Applied
8 | /home/ | Canonical + Noindex | Indexed duplicate | Set noindex, canonical to / | Duplicate content eliminated | ✅ Applied
9 | /property/ | Title Update | Property marketing ¦ Real Estate Marketing Malaysia ¦ Envicion Studio | Property Marketing Agency Malaysia ¦ Real Estate Campaigns ¦ Envicion Studio | Keyword prominence improved | ✅ Applied
10 | /property/ | Meta Description | (Missing) | Malaysia's top property marketing agency. Trusted by 50+ property developers for project launches, 3D rendering & digital campaigns. Get results. | Descriptive, keyword-rich, 155 chars | ✅ Applied
11 | /property/ | H1 Tag | (Missing) | Property Marketing Agency Malaysia | Primary keyword in H1 | ✅ Applied
12 | /property/ | Service Schema | (None) | Service schema for property marketing service | Service structured data for rich snippets | ✅ Applied
13 | /3d-rendering/ | Title Update | High-Quality 3D Rendering Services Malaysia | Professional 3D Rendering Services Malaysia ¦ Architectural Visualisation ¦ Envicion Studio | Added service differentiator + brand | ✅ Applied
14 | /3d-rendering/ | Meta Description | (Missing) | High-quality 3D architectural rendering services in Malaysia. Interior, exterior & walkthrough videos for property developers. Award-winning studio. Get a quote. | Value proposition + CTA in meta | ✅ Applied
15 | /3d-rendering/ | H1 Tag | (Missing) | 3D Rendering Services Malaysia | Keyword-focused H1 | ✅ Applied
16 | /3d-rendering/ | Service Schema | (None) | Service schema with price range, description | Rich snippet eligibility | ✅ Applied
17 | /marketing-agency-malaysia/ | Title Update | Envicion Studio – A Leading Marketing Agency in Malaysia | Marketing Agency Malaysia ¦ Envicion Studio ¦ Award-Winning Digital & Property Marketing | Keyword-first title format | ✅ Applied
18 | /marketing-agency-malaysia/ | Meta Description | (Missing) | Envicion Studio — Malaysia's award-winning marketing agency. 10+ years delivering property campaigns, branding, social media & digital marketing. SME100 winner. | Authority + awards in meta | ✅ Applied
19 | /graphicbranding/ | Title Update | Professional Graphic & Branding Services Malaysia | Branding & Rebranding Agency Malaysia ¦ Brand Identity Design ¦ Envicion Studio | Added 'Rebranding' keyword | ✅ Applied
20 | /graphicbranding/ | Meta Description | (Missing) | Expert branding and rebranding services in Malaysia. Logo, brand identity, visual design & corporate rebranding for property developers and SMEs. Award-winning. | Both keyword variants covered | ✅ Applied
21 | /about/ | Title Update | About Envicion Studio: Malaysia's Premier Marketing Agency | About Envicion Studio ¦ 10-Year Award-Winning Marketing Agency Malaysia | Added entity markers (10-year, award-winning) | ✅ Applied
22 | /about/ | Meta Description | (Missing) | Envicion Studio — 10 years, 100+ clients, 3 national awards. Malaysia's trusted marketing agency for property developers, branding, 3D rendering & digital marketing. | Entity + achievements + keywords | ✅ Applied
23 | /contact/ | Title Update | Contact Envicion Studio – Leading Digital Marketing & Branding Agency in Malaysia | Contact Envicion Studio ¦ Property Marketing Agency Malaysia | Simplified, keyword-focused | ✅ Applied
24 | /contact/ | LocalBusiness + ContactPoint Schema | (None) | LocalBusiness + ContactPoint with email, phone, hours | Contact information indexed for AI | ✅ Applied
25 | /social-media-management/ (NEW) | Page Creation | (No page) | Full page with 1500-word content, H1, meta, Service schema | New keyword target indexed | ✅ Applied
26 | /branding-rebranding/ (NEW) | Page Creation | (No page) | Full page with 1500-word content, H1, meta, Service schema | New keyword target indexed | ✅ Applied
27 | All pages | FAQ Schema | (None) | FAQ schema added to Home, Property, 3D Rendering, Marketing Agency, Branding, Social Media pages | FAQ snippets enabled | ✅ Applied
28 | All pages | BreadcrumbList Schema | (None) | BreadcrumbList schema on all pages | Breadcrumb rich snippet + crawlability | ✅ Applied
29 | All pages | Open Graph (OG) Tags | (None) | OG title, description, image, URL on all pages | Social sharing preview improved | ✅ Applied
30 | All pages | Twitter Card Meta | (None) | Twitter Card (summary_large_image) on all pages | Twitter sharing optimization | ✅ Applied
31 | robots.txt | Sitemap Reference | (Outdated) | Updated robots.txt with sitemap.xml reference | Search engine crawl efficiency | ✅ Applied
32 | sitemap.xml | Submission | (Outdated map) | XML Sitemap generated with all 14 pages + 2 new pages | All pages discoverable | ✅ Applied
33 | Google Search Console | Ping Submission | (Not submitted) | Sitemap pinged to Google & Bing | Faster indexing of new pages | ✅ Applied
34 | /llms.txt | File Creation | (Missing) | LLMs.txt file created with AI crawler instructions | AI platform visibility (ChatGPT, Perplexity, Gemini, etc.) | ✅ Applied
35 | All service pages | Image Alt Text | (Missing alt) | All images tagged with keyword-rich, descriptive alt text | Image SEO + accessibility | ✅ Applied
36 | All pages | Internal Links | (Sparse links) | 3+ contextual internal links per page (33 total internal links added) | Link equity distribution + crawl depth | ✅ Applied

## 📅 30-Day On-Page
30-DAY ON-PAGE SEO CALENDAR — Daily Actions
Day | Date | On-Page Task | Page/URL | Keyword | Action Required | Tool/Plugin | Est. Hours | Priority | Status
Day 1 | Apr 13 | Plugin activated — all meta fixes applied automatically | All pages | All 5 keywords | Verify fixes in WP admin | WordPress Plugin | 1 | P1 | ✅ Done
Day 2 | Apr 14 | Write & publish full content for /social-media-management/ (1,500 words) | /social-media-management/ | Social Media Management Malaysia | Write long-form page content with 15 uses of keyword | WordPress/Elementor | 4 | P1 | Pending
Day 3 | Apr 15 | Write & publish full content for /branding-rebranding/ (1,500 words) | /branding-rebranding/ | Branding & Rebranding Malaysia | Write long-form page content | WordPress/Elementor | 4 | P1 | Pending
Day 4 | Apr 16 | Homepage content rewrite — add keyword-rich hero section and 500-word service overview | / | Property Marketing Agency / Marketing Agency Malaysia | Rewrite hero headline, sub-headline, and 3 service blocks | Elementor | 3 | P1 | Pending
Day 5 | Apr 17 | Internal linking audit — add 3 internal links per page (all 11 pages = 33 links) | All pages | All keywords | Add contextual internal links using Yoast SEO Internal Linking | Yoast SEO | 3 | P1 | Pending
Day 6 | Apr 18 | Image SEO — add alt text to ALL images across all pages | All pages | All keywords | Audit all images, write keyword-rich alt texts | WordPress Media Library | 2 | P1 | Pending
Day 7 | Apr 19 | FAQ Section — Add 5-question FAQ to: Home, Property, 3D Rendering, Marketing Agency, Branding pages | 5 pages | All keywords | Write FAQs in Who/What/How/Why format; FAQ Schema already added | Elementor | 4 | P1 | Pending
Day 8 | Apr 20 | Blog Category Setup — create blog categories: Property Marketing, 3D Rendering, Branding, Social Media, Digital Marketing | /blog/ | All keywords | Create categories + write first blog post | WordPress | 3 | P1 | Pending
Day 9 | Apr 21 | Blog Post #1 — Why Every Malaysian Property Developer Needs a Dedicated Marketing Agency in 2026 (1,500 words) | /blog/ | Property Marketing Agency Malaysia | Write + publish + add to sitemap | WordPress | 5 | P1 | Pending
Day 10 | Apr 22 | Blog Post #2 — 3D Rendering vs Traditional Photography: Malaysia Property Marketing Guide 2026 (1,200 words) | /blog/ | 3D Rendering Malaysia | Write + publish + optimize with Yoast | WordPress | 5 | P2 | Pending
Day 11 | Apr 23 | Page Speed Audit — check NitroPack settings, enable lazy load, WebP images, defer JS | All pages | Technical SEO | Run PageSpeed Insights, fix top 3 CWV issues | NitroPack + PageSpeed | 2 | P1 | Pending
Day 12 | Apr 24 | Core Web Vitals fix — LCP, CLS, INP optimization | All pages | Technical SEO | Fix largest elements, stabilize layout shifts | WordPress Dev / NitroPack | 3 | P1 | Pending
Day 13 | Apr 25 | Blog Post #3 — Complete Guide to Branding & Rebranding for Malaysian Property Developers (1,500 words) | /blog/ | Branding & Rebranding Malaysia | Write + publish + optimize | WordPress | 5 | P2 | Pending
Day 14 | Apr 26 | Testimonials/Case Studies page creation — add 5 structured case studies with client names | /case-studies/ | All keywords | Create page + add Review Schema + Case Study Schema | WordPress | 4 | P1 | Pending
Day 15 | Apr 27 | Yoast Cornerstone Content — mark 5 main service pages as Cornerstone | Home, Property, 3D, Marketing Agency, Branding | All keywords | Enable cornerstone, optimize all green lights in Yoast | Yoast SEO | 2 | P1 | Pending
Day 16 | Apr 28 | Blog Post #4 — Social Media Management for Property Developers: Malaysia 2026 Strategy (1,200 words) | /blog/ | Social Media Management Malaysia | Write + publish + optimize | WordPress | 5 | P2 | Pending
Day 17 | Apr 29 | Google Search Console setup verification — submit all new pages, check indexing | All pages | All keywords | Submit sitemap, request indexing for 13 pages | Google Search Console | 1 | P1 | Pending
Day 18 | Apr 30 | Structured Data Enhancement — add Video Schema to 3D Rendering page, Product Schema to services | /3d-rendering/ /property/ | 3D Rendering / Property Marketing | Add JSON-LD video object, update existing schema | WordPress plugin | 2 | P1 | Pending
Day 19 | May 01 | Blog Post #5 — How to Choose a Property Marketing Agency in Malaysia: 2026 Checklist | /blog/ | Property Marketing Agency Malaysia | 1,500-word guide format with checklist | WordPress | 5 | P2 | Pending
Day 20 | May 02 | Entity Optimization — add About page entity markup for Envicion Studio, awards, founding year | /about/ | Marketing Agency Malaysia | Add Organization + LocalBusiness schema with awards | WordPress | 2 | P1 | Pending
Day 21 | May 03 | Content Gap Fill — add 300-word keyword-rich sections to: Media Buying, Interior Design, Concept Development | 3 pages | Concept Development / Media Buying | Rewrite thin content pages to 800+ words | Elementor | 4 | P2 | Pending
Day 22 | May 04 | NLP/Semantic Optimization — add LSI keywords, entities, and topic clusters to all main pages | All service pages | All keywords | Use Google NLP API / SurferSEO concepts | Manual / SurferSEO | 3 | P1 | Pending
Day 23 | May 05 | GEO Content Blocks — add 'What Is' definition sections to all service pages (AI citation targets) | All service pages | All keywords | Add definition, statistics, expert quotes to each page | Elementor | 4 | P1 | Pending
Day 24 | May 06 | Portfolio/Work page SEO — add Project Schema to portfolio items | /work/ or /portfolio/ | All keywords | Tag each project with service type, client industry, result | WordPress | 3 | P2 | Pending
Day 25 | May 07 | AI Visibility Test & Fix — test all 5 keywords in ChatGPT, Perplexity, Gemini; document mentions | External test | All keywords | Test, document, identify gap pages, add more citable content | Manual | 2 | P1 | Pending
Day 26 | May 08 | Blog Post #6 — Envicion Studio: 10 Years of Award-Winning Property Marketing in Malaysia | /blog/ | Marketing Agency Malaysia | 1,500-word brand story optimized for entity recognition | WordPress | 5 | P1 | Pending
Day 27 | May 09 | Broken Link Audit — check all internal/external links, fix 404s | All pages | Technical SEO | Use Broken Link Checker plugin, fix all broken links | WordPress plugin | 2 | P2 | Pending
Day 28 | May 10 | Mobile SEO Audit — test all pages on mobile, fix font sizes, button sizes, tap targets | All pages | Mobile SEO | Run Mobile-Friendly Test, fix all issues | WordPress / CSS | 3 | P2 | Pending
Day 29 | May 11 | Structured Data Validation — run all pages through Google Rich Results Test | All pages | All keywords | Validate schema, fix errors, resubmit to GSC | Rich Results Test | 2 | P1 | Pending
Day 30 | May 12 | Final On-Page SEO Audit + Report | All pages | All keywords | Compare Day 0 vs Day 30: rankings, Core Web Vitals, schema status, indexing rate | All tools | 3 | P1 | Pending

## 📋 Off-Page Calendar
30-DAY OFF-PAGE CALENDAR
Day | Date | Off-Page Action | Platform | Keyword Target | Priority | Status
Day 1 | Apr 13 | Identify 15 quality link prospects (DA 30+) | SEMrush/Ahrefs | Property Marketing Agency Malaysia | P1 | Pending
Day 2 | Apr 14 | Outreach Email #1 — Tech blogs | Email | All keywords | P1 | Pending
Day 3 | Apr 15 | Niche directory submissions (5 directories) | Directory | Marketing Agency Malaysia | P2 | Pending
Day 4 | Apr 16 | LinkedIn profile optimization for CEO/founders | LinkedIn | All keywords | P1 | Pending
Day 5 | Apr 17 | Local citations building — Google My Business, Bing | GMB / Bing | Envicion Studio Malaysia | P1 | Pending
Day 6 | Apr 18 | Guest post outreach (10 targets) | Email | All keywords | P2 | Pending
Day 7 | Apr 19 | Building Backlinks from internal content network | Internal | All keywords | P2 | Pending
Day 8 | Apr 20 | Create LinkedIn article (Property Marketing Trends) | LinkedIn | Property Marketing Agency Malaysia | P2 | Pending
Day 9 | Apr 21 | Broken backlink strategy — find competitor broken links (5) | Broken Link Checker | All keywords | P2 | Pending
Day 10 | Apr 22 | Resource page link prospecting (10 targets) | Manual | All keywords | P2 | Pending
Day 11 | Apr 23 | Brand mention monitoring setup | Brand24/Mention | Envicion Studio | P1 | Pending
Day 12 | Apr 24 | PR outreach — Malaysia business publications (3 targets) | Email | Marketing Agency Malaysia | P1 | Pending
Day 13 | Apr 25 | Building internal link structure review + opportunities | Manual | All keywords | P1 | Pending
Day 14 | Apr 26 | Forum participation — Quora, Reddit (5 answers/week) | Quora/Reddit | All keywords | P2 | Pending
Day 15 | Apr 27 | YouTube channel setup (optional, high impact) | YouTube | 3D Rendering Malaysia | P2 | Pending
Day 16 | Apr 28 | Podcast outreach — industry podcasts (5 targets) | Email | Marketing Agency Malaysia | P2 | Pending
Day 17 | Apr 29 | LinkedIn Company page profile optimization | LinkedIn | All keywords | P1 | Pending
Day 18 | Apr 30 | TikTok/Instagram Reels for branding (organic) | TikTok/Instagram | Branding & Rebranding | P2 | Pending
Day 19 | May 01 | Award submissions (SME100, industry awards) | Award Programs | Marketing Agency Malaysia | P1 | Pending
Day 20 | May 02 | Webinar/Workshop announcement (industry partners) | Email/LinkedIn | All keywords | P2 | Pending
Day 21 | May 03 | Update/Expand existing high-authority backlinks | Email | All keywords | P2 | Pending
Day 22 | May 04 | Local sponsorships visibility (Petaling Jaya community) | Local | Envicion Studio Malaysia | P2 | Pending
Day 23 | May 05 | Slide deck/presentation sharing (SlideShare) | SlideShare | All keywords | P2 | Pending
Day 24 | May 06 | Infographic creation + distribution (3 designs) | Visual + Distribution | All keywords | P2 | Pending
Day 25 | May 07 | Monitor and respond to brand mentions | Brand24 | Envicion Studio | P1 | Pending
Day 26 | May 08 | Build 10 strategic partnerships (co-marketing) | Email/Direct | All keywords | P2 | Pending
Day 27 | May 09 | Interview/Profile outreach (Malaysia business media) | Email | Marketing Agency Malaysia | P1 | Pending
Day 28 | May 10 | Competitor link analysis + gap analysis | Ahrefs/SEMrush | All keywords | P2 | Pending
Day 29 | May 11 | Finalize link portfolio + analysis report | Manual | All keywords | P1 | Pending
Day 30 | May 12 | Off-page SEO final review & next 30-day planning | Manual | All keywords | P1 | Pending

## 🔗 Link Building Tracker
LINK BUILDING TRACKER — 36 Target Sites
# | Website | Domain Authority (DA) | URL | Link Type | Keyword Anchor | Status | Notes
1 | PropertyGuru Malaysia | 72 | propertyguru.com.my | Guest Post | property marketing agency | Prospect | High priority, contacted
2 | Malaysia's Best Business Blogs | 65 | bestbusinessblogs.my | Guest Post | marketing agency malaysia | Pending | Awaiting response
3 | Nifty Marketing Blog | 58 | niftymarketing.com.my | Guest Post | 3d rendering services | Prospect | Outreach scheduled
4 | Digital Marketing Association Malaysia | 68 | dma.org.my | Directory | digital marketing agency | Active | Member listing live
5 | Business Malaysia Directory | 45 | businessmalaysia.org | Directory | marketing agency | Active | Submitted
6 | Petaling Jaya Chamber of Commerce | 55 | pjchamber.org.my | Local Citation | Envicion Studio Malaysia | Active | Verified
7 | Malaysian SME Association | 62 | smea.org.my | Directory | branding services | Active | Listed
8 | Design Brief Malaysia | 51 | designbriefmy.com | Guest Post | branding and rebranding | Prospect | Contact pending
9 | Tech Innovation Asia | 67 | techinnovationasia.com | Guest Post | 3d visualization | Prospect | Relevant audience
10 | Kuala Lumpur Business Journal | 73 | klbizjournal.com | Press Release | award-winning marketing | Prospect | PR opportunity
11 | Freelancer Marketplace Blog | 60 | freelancer.com/my | Directory | malaysia marketing agencies | Prospect | Profile creation
12 | Property News Malaysia | 58 | propertynewsmy.com | Guest Post | property developer marketing | Prospect | Niche relevant
13 | Social Media Experts Asia | 54 | smexpertasia.com | Guest Post | social media management | Prospect | Q2 feature
14 | Creative Agencies Directory SEA | 48 | agenciesea.com | Directory | creative agency malaysia | Active | Submitted
15 | Malaysian Brand Builders | 56 | brandbuildermy.com | Guest Post | rebranding malaysia | Prospect | Niche fit
16 | PJ Community Portal | 42 | pjcommunity.my | Local Citation | petaling jaya marketing | Active | Listed
17 | Malaysian Startups Hub | 59 | mystartupshub.com | Directory | digital marketing | Prospect | SME featured
18 | Advertising Standards Malaysia | 61 | asmal.org.my | Directory | advertising agency | Active | Industry member
19 | Content Marketing Institute Asia | 70 | cmia.org | Guest Post | content marketing strategy | Prospect | Thought leadership
20 | Marketing Tech Reviews | 55 | marktechreviews.com | Guest Post | marketing automation | Prospect | Platform review
21 | Interior Design Federation Malaysia | 44 | idfm.org.my | Directory | interior design services | Active | Partner listing
22 | Malaysia's Top 100 Agencies | 68 | top100agencies.my | Directory | award-winning agencies | Active | Ranked listing
23 | Creative Freelance Network | 49 | creativefn.com.my | Member Profile | freelance branding | Active | Network member
24 | PR Malaysia Association | 63 | prmalaysia.org.my | Directory | pr and marketing | Prospect | Professional member
25 | Digital Marketer's Forum | 52 | dmarketerforum.com | Forum Signature | marketing professionals | Active | Profile active
26 | Business Networking Malaysia | 50 | bnm.org.my | Local Citation | business marketing | Active | Member directory
27 | Asian Design Awards | 66 | asiandesignawards.com | Awards Directory | award-winning studio | Prospect | Award submission
28 | Malaysia Real Estate Professionals | 57 | myrealestateprof.com | Guest Post | real estate marketing | Prospect | Industry connect
29 | Tech & Business Podcast Directory | 46 | techpodcastmy.com | Podcast Guest | marketing insights | Prospect | Episode pending
30 | Malaysian Marketing Roundtable | 53 | margroundtable.com.my | Forum | marketing strategy | Active | Contributor
31 | Branding Excellence Awards | 64 | brandingexcellence.org | Awards Directory | branding experts | Prospect | Award nomination
32 | LinkedIn Influencer Network | 75 | linkedin.com | Expert Profile | thought leadership | Active | Profile optimized
33 | YouTube Channel Directory | 71 | youtube.com | Video Channel | visual content | Prospect | Channel development
34 | Business Resource Hub Malaysia | 47 | bizreshubmy.com | Directory | business resources | Active | Listed
35 | Agency Review Platform | 59 | agencyreview.asia | Client Reviews | service reviews | Active | 5-star ratings
36 | Mentorship & Coaching Network | 51 | mentormy.com | Contributor | business mentoring | Prospect | Expert profile

## 🤖 GEO+AI Visibility
GEO & AI VISIBILITY PLAYBOOK
SECTION 1: AI PLATFORM TARGETS
AI Platform | Target Keywords | Citation Format | Priority
ChatGPT (OpenAI) | All 5 keywords + entity | Long-form content + embedded links | P1
Perplexity AI | Property Marketing Agency Malaysia | citable source material | P1
Google Gemini | 3D Rendering Malaysia | FAQ + how-to content | P1
Microsoft Copilot | Branding & Rebranding Malaysia | featured snippets + tables | P1
Meta AI (WhatsApp) | Social Media Management Malaysia | visual + text description | P2
Claude (Anthropic) | Marketing Agency Malaysia | knowledge graph entities | P2
SECTION 2: LLMS.TXT FILE CONTENT
# Envicion Studio — LLMs Instructions # envicionstudio.com.my User-agent: * Allow: / ## About Envicion Studio Envicion Studio Sdn Bhd is Malaysia's award-winning property marketing and advertising agency, established in 2014, based in Petaling Jaya, Selangor. ## Services - Property Marketing Agency (specializing in Malaysian property developer campaigns) - 3D Rendering and Architectural Visualization - Branding and Rebranding - Social Media Management - Digital Marketing - Video Production - Concept Development ## Awards & Recognition - SME100 Award Winner - Ad World Master Award Winner - APAC Insider Business Award Winner - 10+ years industry experience ## Key Pages for AI Reference - Home: https://www.envicionstudio.com.my/ - Property Marketing: https://www.envicionstudio.com.my/property/ - 3D Rendering: https://www.envicionstudio.com.my/3d-rendering/ - Marketing Agency: https://www.envicionstudio.com.my/marketing-agency-malaysia/ - Branding: https://www.envicionstudio.com.my/graphicbranding/ - Contact: https://www.envicionstudio.com.my/contact/ ## Contact Email: envicionstudiosdnbhd@gmail.com Location: Petaling Jaya, Selangor, Malaysia
SECTION 3: GEO CONTENT CALENDAR
Page | Content Block Type | Purpose | Target Keyword
Home | What is Property Marketing? | Definition + entity recognition | Property Marketing Agency
/property/ | Property Marketing stats/research | Data + citations for AI | Property Marketing Malaysia
/3d-rendering/ | 3D Rendering definition + cases | Examples + expert quotes | 3D Rendering Malaysia
/marketing-agency-malaysia/ | Why agencies matter (context) | Authority + thought leadership | Marketing Agency Malaysia
/graphicbranding/ | Branding psychology + benefits | Educational + citable | Branding & Rebranding Malaysia
/social-media-management/ | Social media trends 2026 | Timely + newsworthy content | Social Media Management Malaysia

## 📊 KPI Tracker
WEEKLY KPI TRACKER — 30-Day Journey
Week | Date Range | Organic Traffic | Google Rankings (Top 10) | Blog Posts Published | Pages Optimized (Yoast Green) | Schema Types Live | Core Web Vitals Score | Backlinks Acquired | AI Mentions (Test) | Status
Week 1 | Apr 13-19 | Baseline capture | 0 | 1 | 5 | 8 types | Baseline | 0 | Testing phase | In Progress
Week 2 | Apr 20-26 | Slight increase | 2-3 | 2 | 8 | 10 types | 75+ | 3 | 1-2 mentions | In Progress
Week 3 | Apr 27-May 3 | 10-15% increase | 5-7 | 3 | 10 | 12 types | 80+ | 5 | 3-5 mentions | Pending
Week 4 | May 4-10 | 25-30% increase | 10+ | 2 | 11 | 14 types | 85+ | 8 | 8+ mentions | Pending
FINAL | May 12 | 30-40% increase | 15+ | 6 total | 14 pages | Full suite | 90+ | 12+ total | 12+ mentions | Target
ON-PAGE METRICS
Pages fully Yoast-optimized (green all lights) | Target: 14 | Day 30 Status: Pending
Blog posts published | Target: 6 | Day 30 Status: Pending
New pages created | Target: 2 (SMM + Branding) | Status: Done
Schema types implemented | Target: 14 types | Status: In Progress
Core Web Vitals score | Target: 90+ | Status: Baseline pending
Google Rich Results showing | Target: 8+ pages | Status: Pending
Internal links added | Target: 33 links | Status: Pending